# Big Room Planning Facilitation Guide

Big Room Planning (BRP) brings multiple teams together to plan a shared increment of work, surface cross-team dependencies early, and leave with a committed, visualized plan rather than a set of disconnected backlogs.

# Purpose

The event exists to make dependencies visible before they become blockers, not to produce a perfect plan. Treat the output as a starting hypothesis the teams will adjust as they learn.

# Pre-Event Preparation

Two weeks out, confirm the draft feature list with product management and size it roughly against known team capacity. A BRP that opens with an unscoped backlog burns the room's energy on triage instead of planning.

## Room Layout

Seat teams together, not by function, and place a visible program board where every team can post its planned work against a shared timeline. Dependencies get drawn as physical strings or digital links between cards, not tracked in a spreadsheet off to the side.

# Event Agenda

A two-day agenda typically runs: context and vision on day one morning, team breakouts and draft planning through day one afternoon, a management review overnight, and dependency resolution plus final confirmation on day two.

# Facilitation Tips

Keep a visible parking lot for issues that would derail planning if chased in the moment — funding questions, org-design debates, unrelated escalations. Protect the room's focus on the plan itself.

# Common Pitfalls

The most common failure mode is treating the confirmed plan as a fixed commitment rather than the best current view. A close second is under-investing in the pre-event backlog refinement, which pushes scoping work into the room and starves the actual planning conversation of time.